## Burn Down Chart
Project Title: CST361-CLCProject Release #: 3.0 Sprint #: 3.0
| User Story ID | User Story | Task | Assigned To | Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 10
| 1 | Database | Insert device information into dabase | Adam | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2 | RESTful service | Send device info from data generator to Reporting App | Jim | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3 | Update data table | Update data table so it update real time data | Adam | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 4 | Update data chart | Update data table so it display real time data | Jim | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Ideal - Remaining efforts in uninterrupted working hours |  |  |  | 10 | 9 | 8 | 7 | 6 | 5 | 4 | 3 | 2 | 1 | 0
| Actual - Remaining efforts in uninterrupted working hours |  |  |  | 10 | 10 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## How To Use
Step 1 | Hold a Sprint Planning meeting on Day 1 of of your Sprint where you will complete or update your User Stories as well as (re)prioritize your User Stories in your Product Back Log (ideally this should be done for the next 3-4 Sprints)
Step 2 | Copy the User Stories you plan to complete for this Sprint into your Sprint Back Log
Step 3 | Copy the User Stories you plan to complete from your Sprint Back Log into Column C
Step 4 | Break the User Story into a series of step by step development tasks in Column D
Step 5 | Estimate the User Story (in 1, 2, 4 or 8 Effort Man Hours) in Column F and if the task is larger than 8 hours break the User Story into multiple User Stories
Step 6 | Assign the User Story to a single Team Member in Column E
Step 7 | Repeat steps 4-6 for each User Story that has been planned for this Sprint
Step 8 | At the end of each day each Team Member should update the effort hours that were worked on their User Story to burn their work down
Step 9 | After each Daily Standup each Team Member should review the Burn Down Chart to ensure your Sprint will be delivered on time